## Sheet1
Who's Implementing | Related User Story | Task Description | Initial Estimate | Amount Worked on...
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Jake | Create tag | Clean up Create tag so that the UI looks better. | 1 | 1
Jake | Create tag | Change Submit to clear all in creating tag fields | 1 | 1
Jake | Create tag | Change name of Creating tag button to “Add Animal to Track” | 1 | 1
Jake | Create tag | Create tag, add a optional name field that the scientist can add to the tag, so it's clearer what animal is a part of that tag | 1 | 1
Jake | Create tag | Address final concerns with create tag ui | 2 |  | 2
Jake | Server Communication | Python server communication | 2 |  | 2
Mark | View project | Change the View Projects to have Create Project inside of it | 1 | 1 | 1
Mark | Add Sighting | Create GUI for add sightings | 2 |  | 1
Mark | View project | Change the name of view projects button to “projects” | 0.5 | 1
Kenneth | View project data | Clean up the UI for the view project data to better guide the user | 4 | 4
Kenneth | Add Scientist/Remove Scientist | Fix the add scientist button to work on one click instead of just two | 2 | 2
Kenneth | View project data | Change the toString of animal to be role and tagID | 1 |  | 1
Matthew | Cleanup | Remove the scientist class as it is not needed | 3 | 3
Kenneth | Add User | Fix the bug for add user where it will overwrite the existing user | 2 |  | 3
Matthew | Server setup | Add model classes for server | 3 |  | 6
Matthew | Server setup | Python server storage | 7 | 3 |  | 4
Matthew | Cleanup | Helped test python and java sever | 3 |  |  |  | 4
Kenneth | Server communication | Make functionality to handle JSON in java | 8 |  |  | 7 | 7
Jake | Server communication | Make functionality to handle JSON in python | 8 |  |  | 7 | 9
Kenneth & Jake | Server communication | Setup send and receive for server | 4 |  | 4
Kenneth | Server Testing | Testing server requests on the java side | 2 |  |  |  | 3
Kenneth | Server Communication | Added basic client server communication | 2 |  |  | 3
Mark | Add Sighting | Add sighting (select time, animal, location, and add a note) (contributor and guess) (View model and bindings) | 1.5 |  |  |  | 1
Mark | Add Sighting | Make model functionality so that the add sighting class can call it to log it | 1 |  |  | 1
Mark | Testing | Help Test Python and Java for coverage | 3 |  |  |  | 2
|  | Estimate Totals | 66 | 15 | 20 | 22 | 26
|  |  | Estimation Totals | 66 | 66 | 66 | 66
|  |  | Total sums | 15 | 35 | 57 | 83