## Sheet1
Priority | As a… | I want… | So that…
1 | Admin | to log in | I can access the admin specific commands in the system | Milestones
1 | Admin | to be able to add/remove a new research project | Projects can be managed | Login system finished, create projects, add scientist, edit project information
1 | Admin | to be able to add scientist to a project | Scientists can collaborate on research | Add tags and tracking, add description about research to a tagged animal species, visualization
1 | Admin | to be able to remove scientist to a project | So that project access remains accurate and up to date.
1 | Scientist | to be able to add a new animal to be tracked | I can begin observing the animals behavior through its migration patterns | admin filtering?
1 | Scientist | to be able to log in | I can access my research
1 | Scientist | to be able to track my tagged research animal | I can continue to observe the animals behavior through its migration patterns
1 | Admin | to be able to update user roles/Add new Users | they can use the system with the appropriate permissions
2 | Contributor | to be able to log in | I can access my open source contributions
2 | Contributor | to be able to enter tag information | I can help scientist track animals
2 | Guest | to be able to enter tag information without an account | I can help scientist track animals
2 | Admin | I want to view users | I can better understand the user base of the system
2 | Contributor | to be able to view my sent tags information | I can see the research that is linked with my sent tag
2 | Guest | to be able to view my sent tags information on enter | I can see the research that is linked with my sent tag
2 | Scientist | to be able to add a description about my research to a tagged animal species | contributors can get a history of the research with the animal
3 | Admin | to be able to view a log of user changes (added/removed users) | The system user changes can be tracked
3 | Admin | to be able to view a log of tag changes | The system log changes can be tracked
3 | Admin | to be able to assess a contributors data | I can maintain the integrity of open source data
3 | Scientist | to be able to filter/view all my projects | I can easily swap between my projects
3 | Admin | I want to filter users | I can better view the user base of the system
3 | Admin | to filter projects | I can better organize projects
3 | Admin | to filter users | I can better organize users
3 | Admin | to ban users | I can manage what users can access the system
3 | Admin | to unban users | I can lift a ban on the user
3 | Admin
3 | Contributor | to be able to add animal data without a tag on existing projects (open source) | I can contribute to scientific research
3 | Scientist | to be able to visualize my research | I can better understand migration patterns
4 | Transponder | to securly access a project | I can send updates on a tracked animal
4 | Scientist | to be able to add a transponder | I can get immediate tracking updates on animals
| 1 | ASAP
| 2 | Later sprint
| 3 | Nice to have
| 4 | far future