## Sheet1
Who's Implementing | Related User Story | Task Description | Initial Estimate | Amount Worked on…
|  |  |  | Week 1 | Week 2 | Week 3 | Week 4
Jake | Login | Create GUI login | 1 | 1
Jake | Create tag | Create the code behind for the create tag page | 1 | 2
Jake | Create tag | Update GUI to work with updated design | 1 |  |  | 1
Jake | Create tag | Update Codebehind to work with updated GUI | 2 |  |  | 2
Jake | Create tag | Update View model to work with updated codebehind | 1 |  |  | 2
Jake | Create tag | Update business logic to add tags to projects | 1 |  |  |  | 2
Jake | Create tag | Update testing in create tags | 1 |  |  |  | 1
Jake | Create tag | Bind the codebehind to the gui (view) for the create tag page | 1 |  | 1
Jake | Create tag | Create business functionality for create tags | 2 |  | 4
Jake | Create tag | Test create tags business logic | 2 | 3
Jake | Create tag | Update test cases to test updated create tag logic | 1 |  |  | 1
Jake | Create tag | Connect GUI to work with other pages | 2 |  |  |  | 2
Jake, Matthew, Kenny, Mark | Animal Tracking System | Meeting 1 | 2 | 2
Jake, Matthew, Kenny, Mark | Animal Tracking System | Meeting 2 | 3 |  | 3
Jake, Matthew, Kenny, Mark | Animal Tracking System | Meeting 3 | 5 |  |  |  | 5
Kenneth | Create tag / Login / Create Project | Created the data storage class that acted as our data base for the mock server | 3 |  |  | 4
Kenneth | Add User | Create the business functionality for adding a user to the system | 4 |  |  | 5
Kenneth | Add User | Create the Gui for adding a user | 1 |  |  |  | 1
Kenneth | Add User | Create the codebehind for the add user page | 1 |  |  | 1
Kenneth | Add User | Bind the codebehind to the gui (view) for the add user page | 2 |  |  |  | 2
Kenneth | Create Project | Bind the gui to the codebehind (view) for the create project page | 3 |  |  |  | 3
Kenneth | Add/Remove Scientist | Create business functionality for adding and removing a scientist to/from a project | 2 |  |  |  | 2
Kenneth | Add/Remove Scientist | Modify to the codebehind as necessary (functionality could be coupled to admin main page) | 1 |  |  |  | 1
Kenneth | View Project Data | Create the business logic for viewing project data | 1 |  | 3
Kenneth | View Project Data | Create the gui for displaying the project data | 1 | 3
Kenneth | View Project Data | Create the codebehind for the view project data page | 3 | 2 | 1
Kenneth | view project data | Bind the viewmodel to the gui (view) for the view project data page | 2 |  |  |  | 3
Kenneth/Matthew | Fixed .idea being tracked and cleaned up project | design descussion | 1 |  | 2
Mark | Create Project | Create gui for the create project page |  | 1 | 1
Mark | Create Project | Create the business logic for creating a project | 2 |  | 2 | 2
Mark | Delete Project | Create Gui for the delete project page | 1 | 1
Mark | Delete Project | Create Business functionality for deleting a project | 3 |  | 2 | 3
Mark | Delete Project | Create the codebehind for the delete project page | 2 |  |  | 2
Mark | Delete Project | bind the codebehind to the gui (view) for the delete project page | 1 |  |  | 1
Mark/Kenneth | Create Project | Create the code behind for the create project page | 2 |  | 1 |  | 1
Matthew | Login (Admin) | create the admin user | 1 |  |  | 1
Matthew | Login | Create the gui for the start up page | 1 |  | 2
Matthew | Login | Bind the gui to the codebehind (view) for the login page | 1 |  | 2
Matthew | Login | Create business logic for login | 2 |  |  | 3
Matthew | Create tag | Create model implementation for gui | 1 | 1
Matthew | Create tag | Create the gui for the create tag page | 1 | 2
Matthew | Create tag / Login / Create Project | Create storage and local server for data | 4 |  |  | 3 | 5
|  | Estimate Totals | 73 | 18 | 24 | 31 | 28
|  |  | Estimation Totals | 73 | 73 | 73 | 73
|  |  | Total sums | 18 | 42 | 73 | 101