## Sheet1
Who's Implementing | Related User Story | Task Description | Initial Estimate | Amount Worked on...
|  |  |  | Week 1 | Week 2
Mark | add sighting | create the view model and implement it for the add sighting | 4 | 2 | 6
Mark | add sighting | hookup the view for the add sighting page | 1 | 1
Mark | see sighting | Change name of of visualize data to "sighting data" | 1 | 1
Mark | Add sighting | Add a contributor user to have the add sighting button enabled | 0.5 | 0.5
Jake | Add sighting | Add sighting class on python server side | 3 | 3
Jake | Add sighting | Add sighting storage class on python server side | 4 | 1 | 3
Jake | Add sighting | Connect sighting storage and server storage classes | 1 |  | 1
Jake | Server communication | Handle request and create response on python side to add an animal sighting. | 4 |  | 6
Jake | Server Communication | Handle request and create response on python side to retrieve all the sightings for an animal | 4 |  | 6
Matthew | see data | Create the gui for the see data page | 2 | 1
Matthew | see data | Create the view for the see data page | 1 | 1
Matthew | see data | Create and hookup the view model for see data to the view for see data | 4 |  | 5
Kenneth | Server communication | Create request on java side to store an animal sighting | 6 | 6
Kenneth | Server communication | Create response on java side to get the data for an animal sighting | 6 |  | 6
All memebers | Prepopulate server with data | Prepopulating server with data. | 1 |  | 1
All memebers (optional) | Add continue as guest in the login (optional)
All memebers (optional) | Allow guest to option add sighting anonymously (optional)
|  | Estimate Totals | 42.5 | 16.5 | 34
|  |  | Estimation Totals | 42.5 | 42.5
|  |  | Total sums | 16.5 | 50.5